## Ark1
|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week9 | Week 10 | Week 11
Tasks | Status
Kanban project board
planning
Gantt Chart | bar: Week 1
Research and design
Target audience | bar: Week 1
comparing websites | bar: Week 1
Content (pages), user stories | bar: Week 2
Prototype | bar: Week 2
A style guide
Layout/design for mobile | bar: Week 3 to Week 4
Layout/design for other devices | bar: Week 4
Coding | bar: Week 5 to Week 8
Testing | bar: Week 8
Implementation/rollout | bar: Week 10
Safety margin | bar: Week9
Delivery | bar: Week 11